## SetUp
Plan for Master (PM)
1. Set-Up MP Jenkins
2. Connect MP to Slave PCs.
3. Fetch Settings from the user, and run job on targetted Slave PCs
Plan for Resource (PR)
1. Access MP Jenkins, and run Jenkins Countermeasure using Slave PCs resource.
2. Resources do not need to access/login to the Slave machine PCs
to run the jenkins by having a common repository.
Resources
Master (MP)
Slave 1
Slave 3
Slave 2

## Information
PLAN | OTHER DETAILS | Status | Reason
PM1 |  | OK
PM2 |  | OK
PM3 |  | OK
PR1 |  | OK | Basic job configuration only.
PR2 |  | NG | Slave PCs (which are COMMON PCs), according to DTPH-IS, cannot have a folder access to network. Target for common repository: ABG Common Folder
COUNTERMEASURE for PR2:
| Create code to Copy Files from Resource Local to Slave PC | OK | Developers managed to create code to copy environment from Resource's local to Slave PCs machine
LIMITATION of COUNTERMEASURE:
| Initial Coding of the automation (AUTOIT) needs to access the display of the PC in order to run properly. | NG | Jenkins will display an error and will not run properly if run without logging in the machine.
COUNTERMEASURE for LIMITATION:
| 1) Resource must access/login in the slave PC machine. | OK | Tool will run properly
| 2) Code revamp of affected files. | NG | Will take time.

## Status
Tasks | Code | Status | Testing | Logs | Remarks
Changed code so that it could run remotely | Initialization of environment | Done | Done | N/A
| Countermeasure: Comment_Result | Done | Done | Done
| Countermeasure: PL Error | Done | Done | Done
| Countermeasure: StartUp Address | Done | Done | Done
| Countermeasure: Pragma | Done | Done | Done
| Countermeasure: CPU_Emergency | Done | Done | Done
| Countermeasure: Assembler | Done | Done | Done
| Countermeasure: Ambiguous | Done | Done | Done
| Countermeasure: ByteError | On-going | On-going | Done | Memory Error: (1) Byte (4096 Error) (2) 40 subfunc Exceed Only (2) is functioning as per russel, (1) is not yet included in countermeasure code. Magpapatulong ako kay russel, hindi nag ctrl shift s pero nag hihiwalay na ng sheets.
| Rebuild of Software if editing occurs | Done | Done | N/A
Manual creation | TESTER sheet | Done | N/A | N/A
| Developer Sheet | On-going | N/A | N/A
| What to Install | Done | N/A | N/A
| Troubleshooting | On-going | N/A | N/A
Queueing of jobs |  | Done | Done | N/A
Created Users to limit access | TESTER limited access to jenkins. Only build/view jobs. | Done | Done | N/A
| DEVELOPER Create/build/delete jobs. Limited access compared to admin user | Done | Done | N/A
Create Code to copy remote to local after execution of jenkins |  | Done | Done | N/A